## Sheet1
Risk No. | Risk | Description | Hazard | Likelihood | Impact | Solution
Overall
1.1.1 | Updated compability issues | If the new update hasn’t been fully tested on various android devices, this could have various effects, from 'bricked' devices to software issues | Worst case scenario: bricked/unusable devices | 4 | 5 | Test vigourously on older models
1.1.2 | Data restriants | With our new features being very network and security centric, this may burn through a users data allowances | Unhappy users unable to use features and others. | 3 | 3 | Utilise a 3rd party provider, unlimited data packages.
VPN
1.2.1 | Data Requirements/permissions | It might rerquire different accessibilities from various software, apps, personal info. | Poor effectiveness of feature and privacy concerns. | 5 | 3 | Minimal permission requests, store data on cryptic cloud based storage
1.2.2 | Security Concerns | With information pinging of various devices, information could potentially be stored and distributed on other devices. | Privacy infringement, storage concerns | 1 | 5 | store data on cryptic cloud based storage
1.2.3 | Swarm' Compability with non-updated phones | Whilst the newer will have access to this feature, what security and performance concerns are their for non-updated devices, and could it affect the effectiveness of the feature | Poor effectiveness of feature. High battery usage. | 3 | 3 | data load balancing, use comparison to onion routing
Encripted Messages
1.3.1 | Compability with older messages | By including a new method of texting, how can this effect the status of older texts without this new feature | Older messages might not be accessible/Deleted. Can not receive other messages. | 4 | 2 | install backup code, allowing messages from devices without this feature
UI/UX Makeover
1.4.1 | Copyright infringment | If the new UI/UX is similar to exisiting competitor, this could cause conflict and damages | Sued/filed for damages, plagurism ect. | 1 | 5 | Stay within guidelines of patent office, be original
1.4.2 | Performance | The new UI/UX might cause performance issues on older phones, as well as newer, but not optimised devices | Overheating, performance inefficiencies, maybe even legal issues | 2 | 4 | Test vigourously on older models.
NOTE: Likelihood and Impact Scale uses a 1-5 scale, with 1 being not very strong and 5 being very strong